## Sheet1
Tasks | Team Member | Week 1 (6/23) | Week 2 (6/30) | Week 3 (7/7) | Week 3 (7/14) | Week 3 (7/21) | Week 3 (7/28)
Create database tables
User Customer Email Quote Detail | Cameron (Customer ad Email) Charles (Quote Detail and User) | x
Login
Create database access objects | Cameron (Customer ad Email) Charles (Quote Detail and User) | x
Create login page | Austin | x
validation | Austin |  | x
Login functionality (ShowLoginServlet, LoginServlet) | Charles |  | x
Create landing page (Search page) | Austin | x
Add Customer
Create add customer page | Austin |  | x
validation | Austin |  | x
Add customer functionality (ShowAddCustomerServlet, AddCustomerServlet) | Cameron |  | x
Database Access | Cameron/Charles |  | x | x | x | x
Search
Search result page (bottom of landing page) | Austin | x
js validation | Austin |  |  | x
Search by Last Name (ShowSearchServlet) Search by lot number Search by DM customer number | Cameron (last name search) Charles (lot and DM Customer number search) |  |  | x | x
Add New Order
Add new order page | Austin |  |  | x
js validation | Austin |  |  |  | x
Add new order functionality (ShowAddOrderServlet, AddOrderServlet) | Charles |  |  |  | x
Print Items
View printed/printable items page | Austin |  |  |  |  | x
View printable items functionality (ShowPrintItemsServlet) | Cameron |  |  |  |  | x
View printed items functionality (ShowPrintItemsServlet) | Charles |  |  |  |  | x
Testing
Testing/bug fixes | All |  | x | x | x | x | x